## Board
STORIES | NOT DONE | IN PROGRESS... | DONE | DROPPED
STORY # 01 - Task # 01:
3-Tier Sample Project
STORY # 01 - Task # 02:
Use Case Diagram Creation
STORY # 01 - Task # 01:
Gantt Chart Creation
STORY # 01 - Task # 02:
Gantt Chart Creation
STORY # 01 - Task # 03 Diagram Creation
STORY # 01 - Task # 01:
3-Tier Sample Project

## Availability Estimate
Availability Estimate
weekday | M | T | W | R | F | S | S
month | September
Resource | 2019-09-02 | 2019-09-03 | 2019-09-04 | 2019-09-05 | 2019-09-06 | 2019-09-07 | 2019-09-08
Resource | Sprint #1 | [6 empty] | Total per Resource
| 1 | 2 | 3 | 4 | 5 | 6 | 7
Ryan | 2 | 0 | 1 | 2 | 0 |  |  | 5
Evan | 1 | 1 | 2 | 1 | 1 |  |  | 6
Winci | 2 | 2 | 0 | 1 | 0 |  |  | 5
Jake | 0 | 0 | 0 | 0 | 0 |  |  | 0
Ryae | 0 | 0 | 1 | 1 | 2 |  |  | 4
Micaela | 1 | 0 | 1 | 0 | 1 |  |  | 0
Philip | 1 | 0 | 1 | 0 | 0 |  |  | 2
Patrick | 0 | 0 | 1 | 0 | 1 |  |  | 2
Bryan | 0 | 0 | 0 | 0 | 0 |  |  | 0
Total per Day | 7 | 3 | 7 | 5 | 5 | 0 | 0 | 24
Until the end of the Sprint | 20 | 17 | 10 | 5 | 0 | 0 | 0
Total per Sprint | 27

## Actual Spent Time
Actual Availability
weekday | M | T | W | R | F | S | S
month | September
day | 2019-09-02 | 2019-09-03 | 2019-09-04 | 2019-09-05 | 2019-09-06 | 2019-09-07 | 2019-09-08
Resource | Sprint #1 | [6 empty] | Total per Resource
| 1 | 2 | 3 | 4 | 5 | 6 | 7
Ryan | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 4
Evan | 1 | 1 | 2 | 1 | 0 | 0 | 0 | 5
Winci | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 4
Jake | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 2
Ryae | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 3
Micaela | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Philip | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0
Patrick | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 2
Bryan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total per Day | 6 | 3 | 5 | 3 | 1 | 2 | 2 | 20
Until the end of the Sprint | 16 | 13 | 8 | 5 | 4 | 2 | 0
Total per Sprint | 22

## Product BackLog
Product BackLog
Stories
State | Name | Description | Points
Done! | 3-Tier Sample Project | Creation of Bussiness Logic, Database and User Interface for the Login Page | 0
Done! | Diagram Creation | Full Diagram of Project in the means of Use Case and Conceptual Class | 0
Done! | Gantt Chart Creation | Creation of Project Gantt Chart | 0
Note on B2: ====== ID#AAAADpj8NgQ Joana Paulo Pardal (2019-09-08 12:15:20) A prioritized list of high-level requirements.
Note on B4: ====== ID#AAAADpj8NgI INVEST in stories (2019-09-08 12:15:20) - Independent - Negotiable - Valuable - Estimable - Small - Testable

## 1st Sprint
|  |  |  | 26 | M | T | W | R | F | S | S
Story | Task | Category | Who | 5 | Time to finish task (person/hour)
|  |  |  | Estimate | 2019-09-02 | 2019-09-03 | 2019-09-04 | 2019-09-05 | 2019-09-06 | 2019-09-07 | 2019-09-08
Ideal Execution |  |  |  | 20 | 16 | 12 | 8 | 4 | 0 | 0 | 0
Total per Day |  |  |  | 20 | 4 | 3 | 4 | 2 | 2 | 3 | 2
3-Tier Sample Project | Create Bussiness Logic | Presentation | Ryan | 3 | 0 | 2 | 1 | 0 | 0 | 0 | 0
| Generate Database Address | Service | Evan | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
| Create Login User Interface | Service | Winci | 2 | 0 | 0 | 1 | 1 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | M | T | W | R | F | S | S
Diagram Creation | Create Use Case Diagram | Presentation | Miecaela | 3 | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  | Estimate | 2019-09-02 | 2019-09-03 | 2019-09-04 | 2019-09-05 | 2019-09-06 | 2019-09-07 | 2019-09-08
| Create Use Case Diagram | Presentation | Bryan | 2 | 0 | 1 | 0 | 1 | 0 | 0 | 0
| Create Use Case Diagram | Presentation | Patrick | 2 | 1 | 0 | 0 | 0 | 1 | 0 | 0
| Create Conceptual Class Diagram | Distribution | Ryae | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 0
[12 empty] | Ideal | 20 | 16 | 12 | 8 | 4 | 0 | 0 | 0
[12 empty] | Real | 20 | 4 | 3 | 4 | 2 | 2 | 3 | 2
Project Gantt Chart Creation | 1st Sprint and Product Backlog | Presentation | Jake | 2 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | Domain | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1st Sprint and Board | Presentation | Philip | 2 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Service | 3 | 1 | 0 | 1 | 1 | 0 | 0 | 0
| 1st Sprint and Availabilty Estimate | Presentation | Patrick | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Presentation | 11 | 2 | 2 | 3 | 0 | 1 | 1 | 2
[12 empty] | Distribution | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 0
[12 empty] | Testing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | Bug-Fix | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on C3: ====== ID#AAAADpj8NgM SMART Tasks (2019-09-08 12:15:20) - Specific - Measurable - Achievable - Relevant - Time-Boxed

## Check
Fibonnaci | Status | Category | Person
0 | Dropped | Domain | Evan
0.5 | Done! | Service | Bryan
1 | Blocked | Presentation | Jake
2 | Ongoing | Distribution | Micaela
3 | Planned | Testing | Patrick
5 |  | Bug-Fix | Philip
8 |  |  | Ryae
13 |  |  | Ryan
21 |  |  | Winci
34 |  |  | Group 1
55 |  |  | Group 2
89 |  |  | Group 3
144 |  |  | ALL
∞